## Sheet1
Task | Start Date | Days to complete
Topic Selection | 2021-02-24 | 7
Planning | 2021-03-01 | 11
Collection of Research paper | 2021-03-07 | 18
Preparation of Proposal | 2021-03-15 | 12
Requirement Analysis | 2021-03-18 | 13
Coding | 2021-03-29 | 34
Testing | 2021-05-01 | 7
Result Analysis | 2021-05-05 | 4
Report Writing | 2021-03-15 | 58
44251