## Sheet1
Task | Start Day | Days to complete
Topic Selection | 0 | 7
Planning | 7 | 11
Collection of Research Paper | 14 | 18
Preparation of Proposal | 22 | 12
Requirement Analysis | 25 | 14
Coding | 36 | 34
Testing | 65 | 7
Result Analysis | 70 | 4
Report Writing | 22 | 58